## Sheet4
Child Protection Risk Analysis
Organizational Area | Potential Risk | Risk Level | Mitigation Strategy | Lead | Support
Programs
Program design | In program design stage, program team fails to include child protection awareness and capacity building component in program activities which could result in unintentional abuse | medium | Training of program team in CP awareness and CP programs | Technical Support Manager
Program management | Program team members abuse or exploit children | medium | Screening of staff during recruitment | Human Resources Manager
|  |  | Training of program team in CP | Technical Support Manager
Program implementation | Local partners abuse or exploit children | high | Conduct due diligence when choosing local partner organization | Operations Manager
|  |  | train local partners in CP | Technical Support Manager
|  |  | Local partner org staff who support RTP program sign CPP | Program Manager
Local partner organization (NGO, GONGO, gov't) | Local partners lack CP awarness or do not have CP standards/policy |  | Condut thorough due diligence when selecting local partner org | Operations Manager
|  |  | Local partner org staff who support RTP program sign CPP | Program Manager
|  |  | Train local partners in CP | Technical Support Manager
|  |  | Enforce agreement that local partner org must have their own CPP or adopt RTP's CPP as their own as condition of partnership & funding from RTP | Program Manager
|  |  | Provide technical support to local partner org to create their own CPP | Program Manager | Technical Support Manager
Curriculum delivery | child abuse by leaders | high | Training of leaders in CP | Program Manager | Technical Support Manager or RTP Trainers
|  |  | Leaders sign CP policy | Program Manager | Local partner org
|  |  | Regular monitoring of curriculum delivery during follow-up visit | M&E Officer | Program Assistant
| child abuse by children | high | All RTP activities have appropriate supervision | Local partner org | Leaders
Direct service provision | child abuse by caregivers, teachers, community centre volunteers, street centre staff, orphanage workers, etc. | high | All partner orgs sign RTP CPP or develop & enforce their own as condition of partnership with RTP | Program Manager
|  |  | Local partner does appropriate recruitment of direct service providers | Local partner org
|  |  | Regular monitoring of program activities | M&E Officer | Local partner org
|  |  | All direct service providers trained in CP | Program Manager | Technical Support Manager or RTP Trainers
|  |  | All direct service providers sign either RTP or local partner org CPP | Program Manager | Local partner org
Play day events (or other special events such as donor corporate staff engagement) | child abuse by leaders/partners; child abuse by children; child abuse by donors; exploitation of children for media | high | CP policy signed by all parties prior to event | Corporate Staff Engagement Coordinator/Program Manager
|  |  | No 1 adult left alone with children (written in guidelines for event) | Corporate Staff Engagement Coordinator/Program Manager
|  |  | No child left alone with one adult (written in guidelines for event) | Corporate Staff Engagement Coordinator/Program Manager
|  |  | Photograph consent forms signed and filed | Corporate Staff Engagement Coordinator/Program Manager
|  |  | Appropriate selection of participants (ie: donor staff) to participate in play day | Donor
|  |  | RTP staff should be present at event to monitor | Corporate Staff Engagement Coordinator/Program Manager
Donor visit | misrepresentation or exploitation of children; child abuse by adults involved in donor visit | medium | All parties sign CP policy prior to event | Program Manager
|  |  | RTP staff who has been trained in CP is present to monitor the donor visit | Program Manager
|  |  | Donors not allowed to be alone with children (at least 2 people present) | Program Manager | Local partner org
|  |  | Guidelines provided to donor (ie: appropriate about video usage, photo taking, etc.) | Program Manager
Leader training | misrepresentation or inaccurate information that is not inline with CPP given by trainers | low | CP training for all trainers | Technical Support Manager
|  |  | Periodic monitoring of trainings by RTP staff | Technical Support Manager or Program Manager
|  |  | Invite CP experts to training to provide support | Technical Support Manager or Program Manager
|  |  | Ensure trainers know RTP's position on abuse and are required to align with it | Technical Support Manager
|  |  | Trainers sign CPP | Human Resources Manager
Trainer training | misrepresentation or inaccurate information that is not inline with CPP given by trainers | low | CP training for all staff trainers | Technical Support Manager
|  |  | Periodic monitoring of trainings by RTP staff | Program Director or Technical Support Manager
|  |  | Invite CP experts to training to provide support | Technical Support Manager
|  |  | Ensure trainers know RTP's position on abuse and are required to align with it; | Technical Support Manager
|  |  | Trainer trainers sign CPP | Technical Support Manager
Follow-up visits | child abuse by leaders; child abuse by children; child abuse by staff | high | All staff parties sign CP policy | Human Resources Manager
|  |  | All leaders and local partner orgs sign CPP | Operations Manager
|  |  | Children supervised at all times | Leader
Rehab therapy sessions | child abuse by therapists | high | Therapists sign CP policy | Program Manager | Local partner org
|  |  | Local partner signs CP policy | Program Manager
|  |  | CP training for therapists | Program Manager | Technical Support Manager or RTP Trainers
Child-led follow-up activities | child abuse by children; child abuse by leaders | high | Leaders sign CP policy | Program Manager | Local partner org
|  |  | CP training for leaders | Program Manager | Technical Support Manager or RTP Trainers
|  |  | Children supervised at all times | Local partner org | Leaders
|  |  | CP training for children | Program Manager | Technical Support Manager, RTP Trainers, Leaders
Program needs assessments | child abuse by assessors | high | CP policy signed by RTP staff | Human Resources Manager
|  |  | More than one adult present with children | M&E Officer
|  |  | If external assesor then there should be 1 RTP staff who has been trained in CP present | Program Manager
Baseline evaluations | child abuse by evaluators | high | CP policy signed by RTP staff | Human Resources Manager
|  |  | More than one adult present with children | M&E Officer
|  |  | If external assesor then there should be 1 RTP staff who has been trained in CP present | Program Manager
Final evaluations | child abuse by evaluators | high | CP policy signed by RTP staff | Human Resources Manager
|  |  | More than one adult present with children | M&E Officer
|  |  | If external assesor then there should be 1 RTP staff who has been trained in CP present | Program Manager
Program launch ceremonies | child abuse by donors, partners, staff, leaders; manipulation of children for tokenistic child participation (if children present at launch) | high | CP policy signed by all parties prior to event | Program Manager | Operations Manager
|  |  | No 1 adult left alone with children | Program Manager | Local partner org
|  |  | No child left alone with one adult | Program Manager | Leaders
Resource development needs assessments | child abuse by assessors | medium | CP policy signed by assessor | Technical Support Manager
|  |  | More than one adult present during assessment | Technical Support Manager
Facility improvements | child accidents during facility improvements; child abuse by vendors and other adults | low | Facility improvement done when children are not around; no children left alone with vendors | Program Manager | Local partner org
Proposal writing | misrepresentation of children to gain funding | low | Multiple parties review proposal | Program Director
|  |  | Everyone trained in CP | Technical Support Manager
External consultants | lack CP knowledge or knowledge of local situation/reality which could result in inappropriateness | low | Introduce the situation of program area to the experts, including the local customs, living habit, religion, history, level of economic development; | Technical Support Manage | Program Manager
|  |  | External experts must sign CPP as condition of working with RTP | Human Resources Manager
Human Resources
RTP China recruitment | recruitment of staff/volunteer/consultant with child abuse history or tendency | high | Job posting states that RTP China has a CPP to deter potential child abusers from applying | Human Resources Manager
|  |  | Reference checks include CP specific questions | Human Resources Manager
|  |  | Interview includes CP questions | Human Resources Manager
|  |  | All staff/volunteers/consultants sign CPP | Human Resources Manager
|  |  | CP orientation to new staff/volunteers/consultants | Human Resources Manager | Technical Suport Manager
Operations
Policy | policy is not enforced within organization | low | Technical support manager responsibility to have all teams implement CPP policies & procedures | Technical Support Manager | Operations Manager
|  | low | Regular monitoring of CP system by technical support manager or designated person | Technical Support Manager
Procedures | no follow-up for suspected abuse or complaints | low | Designated child protection officer appointed | Technical Support Manager
Office | child abuse occurs in office | medium | Staff/volunteer/consultant will not be allowed to stay with child alone in the office. Minimum 2 people. | Operations Manager or Human Resources Manager
| child abuse occurs at office neighbour | medium | If there is suspected child abuse at our neighbours, approach and share our CPP with them. Inform them that we will call police if it continues. | Human Resources Manager, Operations Manager or Program Director
Documents | files are inappropriate or do not reflect commitment to CP | low | All files reviewed before uploading to program management system | Operations Manager
Child abuse incidents | no follow-up for suspected abuse or complaints | high | All appropriate forms completed & filed confidentially | Designated Child Protection Officer
|  |  | All appropriate parties informed | Designated Child Protection Officer
|  |  | Ensuring process and cases closed out properly and resolved | Designated Child Protection Officer
Due dilligence | due diligence not thorough enough or not does include CP perspective | medium | Add CP components/criteria to due diligence process for selecting local partner orgs | Operations Manager
Communications
Development of communications materials | misrepresentation or exploitation of children in internal communications materials (ie: photos, case studies, articles, annecdotes, etc.) | low | Multiple parties review comms materials | Communications Manager
|  |  | Create communications guidelines | Communications Manager
| child abuse by videographers/photographers/media | high | CPP signed by all vendors (ie: photographers, journalists, videographers, etc.) | Human Resources Manager
|  |  | Vendors not left alone with children | Communications Manager
| children or families do not consent to photos/video | low | Child photo/video consent forms signed by children/guardians | Communications Manager
| key messages from interviews by external parties not in line with CPP and misrepresent reality or are exploitative | medium | RTP staff present during external interviews with children | Communications Manager
|  |  | Media agrees to allow RTP comms manager reviews external materials before publishing and distribution | Communications Manager